## Cash Flow Summary
Prepared by: Mdonahue |  |  | Great Northern Transmission Line
Date: July 14 2014 |  |  | Preliminary Cash Flow
July 14 2014
Revised after MP/MH Agreement
| 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | Totals
Development Phase | 4468849 | 5588081.4762 | 3437003 | 2866670.4 | 1434546.8 | 1343545.6 | 3082549.5 | 675054.4 | 22896300.1762
Line Construction | 0 | 499775.0745 | 6361239.6662 | 60132890.9395 | 149736326.33 | 171981727.2642 | 101360625.5451 | 22517235.3221 | 512589820.1416
Substation Construction | 0 | 0 | 0 | 0 | 378129.2674 | 10155797.7761 | 27839675.5807 | 4620777.3759 | 42994380
GNTL Series Comp Station | 0 | 0 | 0 | 0 | 430800.2369 | 11570434.9438 | 31717562.9396 | 5264421.8797 | 48983220
Capitalized Property Taxes | 0 | 0 | 0 | 0 | 6538338 | 10971942 | 16905078 | 9784642 | 44200000
230 kV Connections | 0 | 0 | 0 | 0 | 40273.4892 | 1081665.5779 | 2965125.8759 | 492146.057 | 4579211
Total Project | 4468849 | 6087856.5507 | 9798242.6662 | 62999561.3395 | 158558414.1235 | 207105113.162 | 183870617.4412 | 43354277.0346 | 676242931.3178
Minnesota Power | 2055670.54 | 2800414.0133 | 4507191.6265 | 28979798.2162 | 72936870.4968 | 95268352.0545 | 84580484.023 | 19942967.4359 | 311071748.4062
MH | 2413178.46 | 3287442.5374 | 5291051.0397 | 34019763.1233 | 85621543.6267 | 111836761.1075 | 99290133.4183 | 23411309.5987 | 365171182.9116
Total Project ($2013) | 4468849 | 6087856.5507 | 9798242.6662 | 62999561.3395 | 158558414.1235 | 207105113.162 | 183870617.4412 | 43354277.0346 | 676242931.3178
With Inflation
Minnesota Power | 2055670.54 | 2842504.908 | 4691494.0817 | 30836111.7281 | 79407164.9559 | 106182307.3611 | 96188649.0651 | 23051957.8765 | 345255860.5164
MH | 2413178.46 | 3336853.5876 | 5507406.0959 | 36198913.7678 | 93217106.6874 | 124648795.5978 | 112917109.772 | 27060994.029 | 405300357.9975
Total Project ($2020 @ 2.5%) | 4468849 | 6179358.4956 | 10198900.1776 | 67035025.4959 | 172624271.6433 | 230831102.9589 | 209105758.8371 | 50112951.9055 | 750556218.5139
LPI IR 025.1 Attachment

## Detail Cash Flow
|  | Year End 2013 | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast |  | Forecast
Grand Total | time axis 2013-12-01 to 2020-06-01
Project Development |  | 4468849 | 32339.75 | 417165 | 451684 | 537170.6933 | 537170.6933 | 537170.6933 | 557347.9754 | 557347.9754 | 557347.9754 | 467778.9067 | 467778.9067 | 467778.9067 | 435833.3333 | 297828.3333 | 297828.3333 | 268100 | 268100 | 268100 | 269404.6667 | 269404.6667 | 269404.6667 | 264333 | 264333 | 264333 | 261385.8667 | 261385.8667 | 261385.8667 | 258735.8667 | 258735.8667 | 258735.8667 | 217717.5333 | 217717.5333 | 217717.5333 | 217717.5333 | 217717.5333 | 217717.5333 | 129747.9667 | 129747.9667 | 129747.9667 | 116144.7667 | 116144.7667 | 116144.7667 | 116144.7667 | 116144.7667 | 116144.7667 | 116144.7667 | 116144.7667 | 116144.7667 | 111962.1333 | 111962.1333 | 111962.1333 | 111962.1333 | 111962.1333 | 111962.1333 | 111962.1333 | 111962.1333 | 111962.1333 | 111962.1333 | 111962.1333 | 111962.1333 | 114246.8333 | 114246.8333 | 114246.8333 | 114246.8333 | 114246.8333 | 114246.8333 | 109646.8333 | 109646.8333 | 109646.8333 | 689376 | 689376 | 689376 | 70229.6667 | 70229.6667 | 70229.6667 | 154788.4667 | 154788.4667 | 154788.4667 |  | 22896300
Line Construction | [8 empty] | 76888.473 | 76888.473 | 76888.473 | 76888.473 | 92266.1676 | 99955.0149 | 102517.964 | 153776.946 | 153776.946 | 205035.928 | 256294.91 | 653552.0205 | 697122.1552 | 740692.2899 | 784262.4246 | 827832.5593 | 871402.694 | 914972.8287 | 2103591.9239 | 2448610.3664 | 7791351.6577 | 4602908.8609 | 6537967.6105 | 2384742.9089 | 6892624.3776 | 5145299.4171 | 9006537.2828 | 6803290.4553 | 4104827.2668 | 2311138.8116 | 8886408.6949 | 7856181.5911 | 13249042.095 | 16024613.7157 | 15249547.145 | 27953307.828 | 5892703.2512 | 3422235.4281 | 11471496.4286 | 13671347.1097 | 12588726.8031 | 13470716.2396 | 14639237.4592 | 13400497.929 | 8690970.3069 | 12072626.3126 | 18845549.6501 | 16533303.9408 | 13322293.9491 | 11755817.6303 | 16790892.409 | 15113061.4577 | 15204953.5399 | 15612522.6796 | 13156043.9389 | 9071132.3034 | 6987857.8726 | 7481174.5824 | 11728383.355 | 4659745.7352 | 4555158.4492 | 5125898.2 | 10588327.2881 | 10221628.8048 | 9098779.0404 | 8686495.9752 | 7220974.4767 | 5138243.9037 | 2673473.504 | 2660341.1658 | 2665467.064 | 2158735.208 |  | 512589820
Line Construction | [8 empty] | 0.015% | 0.015% | 0.015% | 0.015% | 0.018% | 0.0195% | 0.02% | 0.03% | 0.03% | 0.04% | 0.05% | 0.1275% | 0.136% | 0.1445% | 0.153% | 0.1615% | 0.17% | 0.1785% | 0.4104% | 0.4777% | 1.52% | 0.898% | 1.275% | 0.4652% | 1.345% | 1.004% | 1.757% | 1.327% | 0.8008% | 0.4509% | 1.734% | 1.533% | 2.585% | 3.126% | 2.975% | 5.453% | 1.15% | 0.6676% | 2.238% | 2.667% | 2.456% | 2.628% | 2.856% | 2.614% | 1.696% | 2.355% | 3.677% | 3.225% | 2.599% | 2.293% | 3.276% | 2.948% | 2.966% | 3.046% | 2.567% | 1.77% | 1.363% | 1.459% | 2.288% | 0.9091% | 0.8887% | 1% | 2.066% | 1.994% | 1.775% | 1.695% | 1.402% | 1.002% | 0.5216% | 0.519% | 0.52% | 0.44% |  | 100%
Substation Construction | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19060.3369 | 16528.4356 | 11576.0522 | 13781.3804 | 185512.6721 | 24408.4499 | 35753.98 | 35753.98 | 35753.98 | 35753.98 | 35753.98 | 35753.98 | 82261.8168 | 82261.8168 | 82261.8168 | 1854834.7262 | 2024160.9038 | 1877725.5722 | 1877725.5722 | 1369750.8815 | 797552.7296 | 1019169.0069 | 14890187.9764 | 765076.0056 | 726528.8659 | 1340778.0937 | 747710.0063 | 790072.287 | 1326658.6142 | 1326658.6142 | 1326658.6142 | 1745578.7698 | 1834598.7266 | 1512290.3894 | 1326305.1469 | 950980.5653 | 825169.279 | 3015.9977 | 3015.9977 |  | 42994380
GNTL Series Comp Station |  | 2017-04-01: 21715.3189; 2017-05-01: 18830.7402; 2017-06-01: 13188.5217; 2017-07-01: 15701.0379; 2017-08-01: 211353.3915; 2017-09-01: 27808.3897; 2017-10-01: 40734.279; 2017-11-01: 40734.279; 2017-12-01: 40734.279; 2018-01-01: 40734.279; 2018-02-01: 40734.279; 2018-03-01: 40734.279; 2018-04-01: 93720.3576; 2018-05-01: 93720.3576; 2018-06-01: 93720.3576; 2018-07-01: 2113201.2477; 2018-08-01: 2306113.4703; 2018-09-01: 2139280.641; 2018-10-01: 2139280.641; 2018-11-01: 1560548.3502; 2018-12-01: 908646.6839; 2019-01-01: 1161132.6802; 2019-02-01: 16964295.182; 2019-03-01: 871646.1617; 2019-04-01: 827729.6539; 2019-05-01: 1527539.8398; 2019-06-01: 851861.1906; 2019-07-01: 900124.2639; 2019-08-01: 1511453.6077; 2019-09-01: 1511453.6077; 2019-10-01: 1511453.6077; 2019-11-01: 1988726.6407; 2019-12-01: 2090146.5037; 2020-01-01: 1722942.6926; 2020-02-01: 1511050.9048; 2020-03-01: 1083446.0282; 2020-04-01: 940110.0406; 2020-05-01: 3436.1067; 2020-06-01: 3436.1067 |  | 48983220
[12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.04433% | 0.03844% | 0.02692% | 0.03205% | 0.4315% | 0.05677% | 0.08316% | 0.08316% | 0.08316% | 0.08316% | 0.08316% | 0.08316% | 0.1913% | 0.1913% | 0.1913% | 4.314% | 4.708% | 4.367% | 4.367% | 3.186% | 1.855% | 2.37% | 34.63% | 1.779% | 1.69% | 3.118% | 1.739% | 1.838% | 3.086% | 3.086% | 3.086% | 4.06% | 4.267% | 3.517% | 3.085% | 2.212% | 1.919% | 0.007015% | 0.007015%
Capitalized Property Taxes |  | 2017-01-01: 446452; 2017-02-01: 446452; 2017-03-01: 446452; 2017-04-01: 446452; 2017-05-01: 446452; 2017-06-01: 446452; 2017-07-01: 643271; 2017-08-01: 643271; 2017-09-01: 643271; 2017-10-01: 643271; 2017-11-01: 643271; 2017-12-01: 643271; 2018-01-01: 643271; 2018-02-01: 643271; 2018-03-01: 643271; 2018-04-01: 643271; 2018-05-01: 643271; 2018-06-01: 643271; 2018-07-01: 1185386; 2018-08-01: 1185386; 2018-09-01: 1185386; 2018-10-01: 1185386; 2018-11-01: 1185386; 2018-12-01: 1185386; 2019-01-01: 1185386; 2019-02-01: 1185386; 2019-03-01: 1185386; 2019-04-01: 1185386; 2019-05-01: 1185386; 2019-06-01: 1185386; 2019-07-01: 1632127; 2019-08-01: 1632127; 2019-09-01: 1632127; 2019-10-01: 1632127; 2019-11-01: 1632127; 2019-12-01: 1632127; 2020-01-01: 1632127; 2020-02-01: 1632127; 2020-03-01: 1632127; 2020-04-01: 1632127; 2020-05-01: 1632127; 2020-06-01: 1624007 |  | 44200000
230 kV Connections | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2030.0631 | 1760.3974 | 1232.9329 | 1467.8162 | 19758.4351 | 2599.6756 | 3808.0563 | 3808.0563 | 3808.0563 | 3808.0563 | 3808.0563 | 3808.0563 | 8761.4757 | 8761.4757 | 8761.4757 | 197553.2519 | 215587.7088 | 199991.2918 | 199991.2918 | 145888.3302 | 84945.1075 | 108548.8366 | 1585912.2186 | 81486.1026 | 77380.5547 | 142802.5197 | 79636.4987 | 84148.3865 | 141298.6934 | 141298.6934 | 141298.6934 | 185916.706 | 195397.9722 | 161069.8139 | 141261.0466 | 101286.2766 | 87886.4689 | 321.2255 | 321.2255 |  | 4579211
Total Project |  | 4468849 | 32339.75 | 417165 | 451684 | 537170.6933 | 537170.6933 | 537170.6933 | 634236.4484 | 634236.4484 | 634236.4484 | 544667.3797 | 560045.0743 | 567733.9216 | 538351.2973 | 451605.2793 | 451605.2793 | 473135.928 | 524394.91 | 921652.0205 | 966526.8219 | 1010096.9566 | 1053667.0913 | 1092165.5593 | 1135735.694 | 1179305.8287 | 2364977.7905 | 2709996.2331 | 8052737.5244 | 4861644.7276 | 6796703.4772 | 2643478.7755 | 7110341.9109 | 5363016.9504 | 9224254.8162 | 7021007.9887 | 4322544.8001 | 2528856.3449 | 9462608.6615 | 8432381.5578 | 13825242.0617 | 16630016.2013 | 15849263.4849 | 28541902.1014 | 6683069.2524 | 4598275.6935 | 12285728.7105 | 14511059.1917 | 13428438.8851 | 14310428.3216 | 15474766.9079 | 14236027.3776 | 9526499.7555 | 13012603.096 | 19785526.4335 | 17473280.7242 | 18785231.3081 | 17599027.8465 | 22305238.0473 | 20627407.0961 | 19578489.2351 | 18701015.334 | 16744527.296 | 43811160.5137 | 10005698.9758 | 10412446.4903 | 16039136.6414 | 7638586.264 | 8071277.2199 | 9847082.9487 | 15309512.0368 | 15522542.7202 | 15340504.1569 | 15128142.1776 | 12319634.0392 | 9819217.6687 | 6511543.0407 | 6300422.421 | 4459155.8605 | 3944304.0045 | 0 | 676242931
676242931.3178
Minnesota Power |  | 2055670.54 | 14876.285 | 191895.9 | 207774.64 | 247098.5189 | 247098.5189 | 247098.5189 | 291748.7663 | 291748.7663 | 291748.7663 | 250546.9946 | 257620.7342 | 261157.6039 | 247641.5968 | 207738.4285 | 207738.4285 | 217642.5269 | 241221.6586 | 423959.9294 | 444602.3381 | 464644.6 | 484686.862 | 502396.1573 | 522438.4192 | 542480.6812 | 1087889.7837 | 1246598.2672 | 3704259.2612 | 2236356.5747 | 3126483.5995 | 1216000.2367 | 3270757.279 | 2466987.7972 | 4243157.2154 | 3229663.6748 | 1988370.608 | 1163273.9187 | 4352799.9843 | 3878895.5166 | 6359611.3484 | 7649807.4526 | 7290661.2031 | 13129274.9667 | 3074211.8561 | 2115206.819 | 5651435.2068 | 6675087.2282 | 6177081.8872 | 6582797.0279 | 7118392.7776 | 6548572.5937 | 4382189.8876 | 5985797.4241 | 9101342.1594 | 8037709.1331 | 8641206.4017 | 8095552.8094 | 10260409.5018 | 9488607.2642 | 9006105.0482 | 8602467.0537 | 7702482.5561 | 20153133.8363 | 4602621.5289 | 4789725.3856 | 7378002.8551 | 3513749.6815 | 3712787.5211 | 4529658.1564 | 7042375.5369 | 7140369.6513 | 7056631.9122 | 6958945.4017 | 5667031.658 | 4516840.1276 | 2995309.7987 | 2898194.3136 | 2051211.6958 | 1814379.8421 | 0 | 311071748.26
MH |  | 2413178.46 | 17463.465 | 225269.1 | 243909.36 | 290072.1744 | 290072.1744 | 290072.1744 | 342487.6821 | 342487.6821 | 342487.6821 | 294120.385 | 302424.3401 | 306576.3176 | 290709.7006 | 243866.8508 | 243866.8508 | 255493.4011 | 283173.2514 | 497692.0911 | 521924.4838 | 545452.3565 | 568980.2293 | 589769.402 | 613297.2748 | 636825.1475 | 1277088.0069 | 1463397.9659 | 4348478.2632 | 2625288.1529 | 3670219.8777 | 1427478.5388 | 3839584.6319 | 2896029.1532 | 4981097.6007 | 3791344.3139 | 2334174.1921 | 1365582.4263 | 5109808.6772 | 4553486.0412 | 7465630.7133 | 8980208.7487 | 8558602.2818 | 15412627.1348 | 3608857.3963 | 2483068.8745 | 6634293.5037 | 7835971.9635 | 7251356.998 | 7727631.2937 | 8356374.1303 | 7687454.7839 | 5144309.868 | 7026805.6718 | 10684184.2741 | 9435571.5911 | 10144024.9064 | 9503475.0371 | 12044828.5456 | 11138799.8319 | 10572384.187 | 10098548.2804 | 9042044.7398 | 23658026.6774 | 5403077.4469 | 5622721.1048 | 8661133.7864 | 4124836.5826 | 4358489.6987 | 5317424.7923 | 8267136.4999 | 8382173.0689 | 8283872.2447 | 8169196.7759 | 6652602.3812 | 5302377.5411 | 3516233.242 | 3402228.1073 | 2407944.1647 | 2129924.1624 | 0 | 365171180.9116
|  | 4468849 | 32339.75 | 417165 | 451684 | 537170.6933 | 537170.6933 | 537170.6933 | 634236.4484 | 634236.4484 | 634236.4484 | 544667.3797 | 560045.0743 | 567733.9216 | 538351.2973 | 451605.2793 | 451605.2793 | 473135.928 | 524394.91 | 921652.0205 | 966526.8219 | 1010096.9566 | 1053667.0913 | 1092165.5593 | 1135735.694 | 1179305.8287 | 2364977.7905 | 2709996.2331 | 8052737.5244 | 4861644.7276 | 6796703.4772 | 2643478.7755 | 7110341.9109 | 5363016.9504 | 9224254.8162 | 7021007.9887 | 4322544.8001 | 2528856.3449 | 9462608.6615 | 8432381.5578 | 13825242.0617 | 16630016.2013 | 15849263.4849 | 28541902.1014 | 6683069.2524 | 4598275.6935 | 12285728.7105 | 14511059.1917 | 13428438.8851 | 14310428.3216 | 15474766.9079 | 14236027.3776 | 9526499.7555 | 13012603.096 | 19785526.4335 | 17473280.7242 | 18785231.3081 | 17599027.8465 | 22305238.0473 | 20627407.0961 | 19578489.2351 | 18701015.334 | 16744527.296 | 43811160.5137 | 10005698.9758 | 10412446.4903 | 16039136.6414 | 7638586.264 | 8071277.2199 | 9847082.9487 | 15309512.0368 | 15522542.7202 | 15340504.1569 | 15128142.1776 | 12319634.0392 | 9819217.6687 | 6511543.0407 | 6300422.421 | 4459155.8605 | 3944304.0045 | 0 | 676242929.1716
Inflation Factor | 2.5% | 100% | 100.2% | 100.4% | 100.6% | 100.8% | 101% | 101.3% | 101.5% | 101.7% | 101.9% | 102.1% | 102.3% | 102.5% | 102.7% | 102.9% | 103.1% | 103.3% | 103.5% | 103.8% | 104% | 104.2% | 104.4% | 104.6% | 104.8% | 105% | 105.2% | 105.4% | 105.6% | 105.8% | 106% | 106.3% | 106.5% | 106.7% | 106.9% | 107.1% | 107.3% | 107.5% | 107.7% | 107.9% | 108.1% | 108.3% | 108.5% | 108.8% | 109% | 109.2% | 109.4% | 109.6% | 109.8% | 110% | 110.2% | 110.4% | 110.6% | 110.8% | 111% | 111.3% | 111.5% | 111.7% | 111.9% | 112.1% | 112.3% | 112.5% | 112.7% | 112.9% | 113.1% | 113.3% | 113.5% | 113.8% | 114% | 114.2% | 114.4% | 114.6% | 114.8% | 115% | 115.2% | 115.4% | 115.6% | 115.8% | 116% | 116.3%
Minnesota Power |  | 2055670.54 | 14907.2773 | 192695.4663 | 209073.2315 | 249157.6733 | 249672.4618 | 250187.2504 | 296003.4358 | 296611.2457 | 297219.0556 | 255766.7237 | 263524.5427 | 267686.544 | 254348.5567 | 213797.466 | 214230.2544 | 224897.2778 | 249764.9257 | 439858.4268 | 462201.1806 | 484004.7917 | 505891.9122 | 525422.6478 | 547471.9268 | 569604.7153 | 1144550.7099 | 1314122.34 | 3912623.8447 | 2366810.7082 | 3315375.317 | 1292000.2515 | 3481993.6866 | 2631453.6503 | 4534874.274 | 3458431.5184 | 2133355.9649 | 1250519.4626 | 4688328.3164 | 4185974.745 | 6876329.7704 | 8287291.407 | 7913405.1808 | 14278086.5262 | 3349610.0016 | 2309100.7774 | 6181257.2575 | 7314783.0876 | 6781921.1553 | 7241076.7307 | 7845062.0403 | 7230715.5722 | 4847797.5631 | 6634258.8118 | 10106282.0229 | 8941951.4106 | 9631344.6353 | 9040033.9705 | 11478833.1301 | 10635147.3086 | 10113105.4603 | 9677775.4354 | 8681339.7143 | 22756246.9568 | 5206715.6045 | 5428355.437 | 8377107.4084 | 3996890.2627 | 4231030.7793 | 5171359.7285 | 8054717.0203 | 8181673.5588 | 8100425.3825 | 8002787.212 | 6528892.7227 | 5213186.3139 | 3463326.9548 | 3357075.08 | 2380260.2387 | 2109216.5664 |  | 345255860.5164
MH |  | 2413178.46 | 17499.8472 | 226207.7213 | 245433.7935 | 292489.4425 | 293093.7596 | 293698.0766 | 347482.2942 | 348195.8102 | 348909.3262 | 300247.893 | 309354.8979 | 314240.7256 | 298583.0883 | 250979.634 | 251487.6899 | 264009.8478 | 293202.3041 | 516355.5445 | 542583.9946 | 568179.5381 | 593873.1143 | 616800.4996 | 642684.4358 | 668666.4049 | 1343603.0073 | 1542665.3557 | 4593080.1655 | 2778429.9618 | 3891962.3286 | 1516695.9475 | 4087557.806 | 3089097.7634 | 5323548.0608 | 4059897.8694 | 2504374.3936 | 1468001.1082 | 5503689.7628 | 4913970.3528 | 8072213.2088 | 9728559.4778 | 9289649.5601 | 16761232.0091 | 3932150.8714 | 2710683.5213 | 7256258.5197 | 8586919.2767 | 7961385.704 | 8500394.423 | 9209420.6561 | 8488231.3239 | 5690892.7915 | 7788042.9529 | 11863896.2877 | 10497073.3951 | 11306361.0936 | 10612213.7915 | 13475151.9354 | 12484738.1449 | 11871906.41 | 11360866.8154 | 10191137.9255 | 26713855.1232 | 6112231.3618 | 6372417.2521 | 9833995.6533 | 4692001.6127 | 4966862.2192 | 6070726.6379 | 9455537.3717 | 9604573.3081 | 9509195.0142 | 9394576.2923 | 7664352.3267 | 6119827.412 | 4065644.6861 | 3940914.2243 | 2794218.5411 | 2476036.8388 |  | 405300357.9975
Total Project |  | 4468849 | 32407.1245 | 418903.1875 | 454507.025 | 541647.1158 | 542766.2214 | 543885.327 | 643485.7299 | 644807.0559 | 646128.3818 | 556014.6167 | 572879.4406 | 581927.2696 | 552931.645 | 464777.1 | 465717.9443 | 488907.1256 | 542967.2297 | 956213.9713 | 1004785.1752 | 1052184.3298 | 1099765.0265 | 1142223.1474 | 1190156.3627 | 1238271.1201 | 2488153.7171 | 2856787.6957 | 8505704.0102 | 5145240.67 | 7207337.6456 | 2808696.199 | 7569551.4927 | 5720551.4138 | 9858422.3348 | 7518329.3879 | 4637730.3584 | 2718520.5708 | 10192018.0792 | 9099945.0977 | 14948542.9792 | 18015850.8847 | 17203054.7409 | 31039318.5353 | 7281760.873 | 5019784.2988 | 13437515.7771 | 15901702.3643 | 14743306.8593 | 15741471.1537 | 17054482.6964 | 15718946.8961 | 10538690.3546 | 14422301.7647 | 21970178.3106 | 19439024.8057 | 20937705.7289 | 19652247.762 | 24953985.0655 | 23119885.4535 | 21985011.8703 | 21038642.2508 | 18872477.6398 | 49470102.0801 | 11318946.9664 | 11800772.689 | 18211103.0616 | 8688891.8753 | 9197892.9985 | 11242086.3664 | 17510254.3921 | 17786246.8669 | 17609620.3967 | 17397363.5043 | 14193245.0494 | 11333013.726 | 7528971.6409 | 7297989.3043 | 5174478.7798 | 4585253.4052 |  | 750556218.5139
LPI IR 025.1 Attachment