## Cash Flow Summary
Prepared by: Mdonahue |  |  | Great Northern Transmission Line
Date: April 14 2014 |  |  | Preliminary Cash Flow
April 2014
| 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | Totals
Certification Phase | 4468849 | 5588081.4762 | 3437003 | 2866670.4 | 1434546.8 | 1343545.6 | 3570316 | 675054.4 | 23384066.6762
Line Construction | 0 | 500807.0135 | 6374374.3978 | 60257053.748 | 150045502.9306 | 172336836.3223 | 101569915.6647 | 22563729.7057 | 513648219.7826
Blackberry 500/230 kV Substation | 0 | 0 | 0 | 0 | 396473.7484 | 10648493.9405 | 29190283.5466 | 4844948.7645 | 45080200
GNTL Series Comp Station | 0 | 0 | 0 | 0 | 239246.3959 | 6425680.9123 | 17614457.8622 | 2923614.8296 | 27203000
230 kV System Improvements | 0 | 0 | 0 | 0 | 40273.4892 | 1081665.5779 | 2965125.8759 | 492146.057 | 4579211
Total Project | 4468849 | 6088888.4897 | 9811377.3978 | 63123724.148 | 152156043.3641 | 191836222.3529 | 154910098.9494 | 31499493.7568 | 613894697.4587
Minnesota Power | 2279112.99 | 3105333.1302 | 5003802.4792 | 32193099.3753 | 77599582.2692 | 97836473.6916 | 79004150.8953 | 16064743.9332 | 313086298.764
MH | 2189736.01 | 2983555.3594 | 4807574.9186 | 30930624.7727 | 74556461.095 | 93999748.6614 | 75905948.0541 | 15434749.8235 | 300808398.6947
Total Project ($2013) | 4468849 | 6088888.4897 | 9811377.3978 | 63123724.148 | 152156043.3641 | 191836222.3529 | 154910098.9494 | 31499493.7568 | 613894697.4587

## Detail Cash Flow
| Year End 2013 | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast -> | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast |  | Forecast
Grand Total | time axis 2013-12-01 to 2020-06-01
Certification Phase | 4468849 | 32339.75 | 417165 | 451684 | 537170.6933 | 537170.6933 | 537170.6933 | 557347.9754 | 557347.9754 | 557347.9754 | 467778.9067 | 467778.9067 | 467778.9067 | 435833.3333 | 297828.3333 | 297828.3333 | 268100 | 268100 | 268100 | 269404.6667 | 269404.6667 | 269404.6667 | 264333 | 264333 | 264333 | 261385.8667 | 261385.8667 | 261385.8667 | 258735.8667 | 258735.8667 | 258735.8667 | 217717.5333 | 217717.5333 | 217717.5333 | 217717.5333 | 217717.5333 | 217717.5333 | 129747.9667 | 129747.9667 | 129747.9667 | 116144.7667 | 116144.7667 | 116144.7667 | 116144.7667 | 116144.7667 | 116144.7667 | 116144.7667 | 116144.7667 | 116144.7667 | 111962.1333 | 111962.1333 | 111962.1333 | 111962.1333 | 111962.1333 | 111962.1333 | 111962.1333 | 111962.1333 | 111962.1333 | 111962.1333 | 111962.1333 | 111962.1333 | 114246.8333 | 114246.8333 | 114246.8333 | 114246.8333 | 114246.8333 | 114246.8333 | 109646.8333 | 109646.8333 | 109646.8333 | 851964.8333 | 851964.8333 | 851964.8333 | 70229.6667 | 70229.6667 | 70229.6667 | 154788.4667 | 154788.4667 | 154788.4667 |  | 23384066.6762
Line Construction | [7 empty] | 77047.2329 | 77047.2329 | 77047.2329 | 77047.2329 | 92456.6794 | 100161.4027 | 102729.6438 | 154094.4657 | 154094.4657 | 205459.2876 | 256824.1095 | 654901.4792 | 698561.5778 | 742221.6765 | 785881.7751 | 829541.8737 | 873201.9723 | 916862.0709 | 2107935.435 | 2453666.274 | 7807439.2944 | 4612412.9789 | 6551467.2512 | 2389666.9425 | 6906856.316 | 5155923.4668 | 9025134.0432 | 6817337.9364 | 4113302.9425 | 2315910.867 | 8904757.4129 | 7872403.0891 | 13276398.8086 | 16057701.4488 | 15281034.5153 | 28011026.011 | 5904870.5455 | 3429301.6835 | 11495182.8536 | 13699575.8017 | 12614720.0932 | 13498530.6675 | 14669464.6578 | 13428167.3696 | 8708915.4824 | 12097553.9548 | 18884462.0712 | 16567442.021 | 13349801.9136 | 11780091.1237 | 16825562.3596 | 15144267.0114 | 15236348.833 | 15644759.5243 | 13183208.6293 | 9089862.44 | 7002286.4497 | 7496621.7634 | 11752600.2019 | 4669367.2104 | 4564563.9718 | 5136482.19 | 10610190.1394 | 10242734.4946 | 9117566.2622 | 8704431.912 | 7235808.451 | 5148853.3852 | 2678993.7105 | 2665834.2566 | 2670970.7388 | 2163273.1636 |  | 513648219
Line Construction | [7 empty] | 0.015% | 0.015% | 0.015% | 0.015% | 0.018% | 0.0195% | 0.02% | 0.03% | 0.03% | 0.04% | 0.05% | 0.1275% | 0.136% | 0.1445% | 0.153% | 0.1615% | 0.17% | 0.1785% | 0.4104% | 0.4777% | 1.52% | 0.898% | 1.275% | 0.4652% | 1.345% | 1.004% | 1.757% | 1.327% | 0.8008% | 0.4509% | 1.734% | 1.533% | 2.585% | 3.126% | 2.975% | 5.453% | 1.15% | 0.6676% | 2.238% | 2.667% | 2.456% | 2.628% | 2.856% | 2.614% | 1.696% | 2.355% | 3.677% | 3.225% | 2.599% | 2.293% | 3.276% | 2.948% | 2.966% | 3.046% | 2.567% | 1.77% | 1.363% | 1.459% | 2.288% | 0.9091% | 0.8887% | 1% | 2.066% | 1.994% | 1.775% | 1.695% | 1.402% | 1.002% | 0.5216% | 0.519% | 0.52% | 0.44% |  | 100%
Blackberry 500/230 kV Substation | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19985.0259 | 17330.2926 | 12137.6503 | 14449.9673 | 194512.5935 | 25592.5962 | 37488.5409 | 37488.5409 | 37488.5409 | 37488.5409 | 37488.5409 | 37488.5409 | 86252.6486 | 86252.6486 | 86252.6486 | 1944819.7747 | 2122360.6056 | 1968821.1422 | 1968821.1422 | 1436202.6779 | 836245.0292 | 1068612.7505 | 15612567.3172 | 802192.7365 | 761775.5293 | 1405824.3105 | 783984.2469 | 828401.682 | 1391019.8416 | 1391019.8416 | 1391019.8416 | 1830263.3986 | 1923602.0501 | 1585657.3164 | 1390649.2264 | 997116.2296 | 865201.3619 | 3162.3151 | 3162.3151 |  | 45080200
GNTL Series Comp Station | 2017-04-01: 12059.6772; 2017-05-01: 10457.7164; 2017-06-01: 7324.2909; 2017-07-01: 8719.6255; 2017-08-01: 117375.8342; 2017-09-01: 15443.485; 2017-10-01: 22621.9222; 2017-11-01: 22621.9222; 2017-12-01: 22621.9222; 2018-01-01: 22621.9222; 2018-02-01: 22621.9222; 2018-03-01: 22621.9222; 2018-04-01: 52047.9235; 2018-05-01: 52047.9235; 2018-06-01: 52047.9235; 2018-07-01: 1173573.594; 2018-08-01: 1280708.0615; 2018-09-01: 1188056.8749; 2018-10-01: 1188056.8749; 2018-11-01: 866655.9032; 2018-12-01: 504620.0667; 2019-01-01: 644839.0347; 2019-02-01: 9421179.7803; 2019-03-01: 484071.6992; 2019-04-01: 459682.5153; 2019-05-01: 848324.5132; 2019-06-01: 473084.0473; 2019-07-01: 499887.1113; 2019-08-01: 839390.9688; 2019-09-01: 839390.9688; 2019-10-01: 839390.9688; 2019-11-01: 1104446.1921; 2019-12-01: 1160770.0625; 2020-01-01: 956842.1608; 2020-02-01: 839167.3263; 2020-03-01: 601695.4848; 2020-04-01: 522093.3502; 2020-05-01: 1908.2537; 2020-06-01: 1908.2537 |  | 27203000
[11 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.04433% | 0.03844% | 0.02692% | 0.03205% | 0.4315% | 0.05677% | 0.08316% | 0.08316% | 0.08316% | 0.08316% | 0.08316% | 0.08316% | 0.1913% | 0.1913% | 0.1913% | 4.314% | 4.708% | 4.367% | 4.367% | 3.186% | 1.855% | 2.37% | 34.63% | 1.779% | 1.69% | 3.118% | 1.739% | 1.838% | 3.086% | 3.086% | 3.086% | 4.06% | 4.267% | 3.517% | 3.085% | 2.212% | 1.919% | 0.007015% | 0.007015%
230 kV System Improvements | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2030.0631 | 1760.3974 | 1232.9329 | 1467.8162 | 19758.4351 | 2599.6756 | 3808.0563 | 3808.0563 | 3808.0563 | 3808.0563 | 3808.0563 | 3808.0563 | 8761.4757 | 8761.4757 | 8761.4757 | 197553.2519 | 215587.7088 | 199991.2918 | 199991.2918 | 145888.3302 | 84945.1075 | 108548.8366 | 1585912.2186 | 81486.1026 | 77380.5547 | 142802.5197 | 79636.4987 | 84148.3865 | 141298.6934 | 141298.6934 | 141298.6934 | 185916.706 | 195397.9722 | 161069.8139 | 141261.0466 | 101286.2766 | 87886.4689 | 321.2255 | 321.2255 |  | 4579211
Total Project | 4468849 | 32339.75 | 417165 | 451684 | 537170.6933 | 537170.6933 | 537170.6933 | 634395.2084 | 634395.2084 | 634395.2084 | 544826.1397 | 560235.5863 | 567940.3096 | 538562.9773 | 451922.7993 | 451922.7993 | 473559.288 | 524924.11 | 923001.4805 | 967966.2459 | 1011626.3446 | 1055286.4433 | 1093874.8753 | 1137534.974 | 1181195.0727 | 2369321.3058 | 2715052.1455 | 8068825.1763 | 4871148.8546 | 6810203.1306 | 2648402.8138 | 7124573.8628 | 5373641.0102 | 9242851.5941 | 7035055.483 | 4331020.4838 | 2533628.4048 | 9034505.3969 | 8002151.0711 | 13406146.8011 | 16207921.0133 | 15426727.7185 | 28147865.7066 | 6045652.7331 | 3877093.324 | 11654963.4001 | 13879639.1152 | 12794783.4046 | 13678593.9806 | 14845345.3399 | 13604048.0493 | 8884796.1528 | 12356578.1614 | 19143486.2911 | 16826466.2363 | 16777710.7366 | 15510709.703 | 20294393.8783 | 18613098.5268 | 17797057.9391 | 17182531.9101 | 15119456.1337 | 35823768.9535 | 8484283.8528 | 8909707.2275 | 14263798.4327 | 6120318.863 | 6086648.0123 | 7617838.5681 | 13091546.5281 | 13466408.8826 | 13090157.4505 | 12836166.8898 | 10009607.458 | 7590160.692 | 4449321.3955 | 4295803.9287 | 2831151.005 | 2323453.429 | 0 | 613894696.6762
Minnesota Power | 2279112.99 | 16493.2725 | 212754.15 | 230358.84 | 273957.0536 | 273957.0536 | 273957.0536 | 323541.5563 | 323541.5563 | 323541.5563 | 277861.3312 | 285720.149 | 289649.5579 | 274667.1184 | 230480.6277 | 230480.6277 | 241515.2369 | 267711.2961 | 470730.7551 | 493662.7854 | 515929.4357 | 538196.0861 | 557876.1864 | 580142.8367 | 602409.4871 | 1208353.8659 | 1384676.5942 | 4115100.8399 | 2484285.9158 | 3473203.5966 | 1350685.435 | 3633532.67 | 2740556.9152 | 4713854.313 | 3587878.2964 | 2208820.4467 | 1292150.4865 | 4607597.7524 | 4081097.0463 | 6837134.8686 | 8266039.7168 | 7867631.1364 | 14355411.5104 | 3083282.8939 | 1977317.5952 | 5944031.334 | 7078615.9487 | 6525339.5363 | 6976082.9301 | 7571126.1233 | 6938064.5051 | 4531246.0379 | 6301854.8623 | 9763178.0084 | 8581497.7805 | 8556632.4757 | 7910461.9485 | 10350140.8779 | 9492680.2487 | 9076499.5489 | 8763091.2741 | 7710922.6282 | 18270122.1663 | 4326984.7649 | 4543950.686 | 7274537.2007 | 3121362.6201 | 3104190.4863 | 3885097.6697 | 6676688.7293 | 6867868.5301 | 6675980.2998 | 6546445.1138 | 5104899.8036 | 3870981.9529 | 2269153.9117 | 2190860.0036 | 1443887.0126 | 1184961.2488 | 0 | 313086295.3048
MH | 2189736.01 | 15846.4775 | 204410.85 | 221325.16 | 263213.6397 | 263213.6397 | 263213.6397 | 310853.6521 | 310853.6521 | 310853.6521 | 266964.8084 | 274515.4373 | 278290.7517 | 263895.8589 | 221442.1717 | 221442.1717 | 232044.0511 | 257212.8139 | 452270.7254 | 474303.4605 | 495696.9088 | 517090.3572 | 535998.6889 | 557392.1373 | 578785.5856 | 1160967.4398 | 1330375.5513 | 3953724.3364 | 2386862.9387 | 3336999.534 | 1297717.3788 | 3491041.1928 | 2633084.095 | 4528997.2811 | 3447177.1867 | 2122200.0371 | 1241477.9184 | 4426907.6445 | 3921054.0248 | 6569011.9326 | 7941881.2965 | 7559096.5821 | 13792454.1962 | 2962369.8392 | 1899775.7288 | 5710932.066 | 6801023.1664 | 6269443.8682 | 6702511.0505 | 7274219.2165 | 6665983.5441 | 4353550.1149 | 6054723.2991 | 9380308.2826 | 8244968.4558 | 8221078.2609 | 7600247.7545 | 9944253.0004 | 9120418.2781 | 8720558.3902 | 8419440.6359 | 7408533.5055 | 17553646.7872 | 4157299.0879 | 4365756.5415 | 6989261.232 | 2998956.2429 | 2982457.526 | 3732740.8984 | 6414857.7988 | 6598540.3525 | 6414177.1508 | 6289721.776 | 4904707.6544 | 3719178.7391 | 2180167.4838 | 2104943.925 | 1387263.9925 | 1138492.1802 | 0 | 300808402.6948
| 4468849 | 32339.75 | 417165 | 451684 | 537170.6933 | 537170.6933 | 537170.6933 | 634395.2084 | 634395.2084 | 634395.2084 | 544826.1397 | 560235.5863 | 567940.3096 | 538562.9773 | 451922.7993 | 451922.7993 | 473559.288 | 524924.11 | 923001.4805 | 967966.2459 | 1011626.3446 | 1055286.4433 | 1093874.8753 | 1137534.974 | 1181195.0727 | 2369321.3058 | 2715052.1455 | 8068825.1763 | 4871148.8546 | 6810203.1306 | 2648402.8138 | 7124573.8628 | 5373641.0102 | 9242851.5941 | 7035055.483 | 4331020.4838 | 2533628.4048 | 9034505.3969 | 8002151.0711 | 13406146.8011 | 16207921.0133 | 15426727.7185 | 28147865.7066 | 6045652.7331 | 3877093.324 | 11654963.4001 | 13879639.1152 | 12794783.4046 | 13678593.9806 | 14845345.3399 | 13604048.0493 | 8884796.1528 | 12356578.1614 | 19143486.2911 | 16826466.2363 | 16777710.7366 | 15510709.703 | 20294393.8783 | 18613098.5268 | 17797057.9391 | 17182531.9101 | 15119456.1337 | 35823768.9535 | 8484283.8528 | 8909707.2275 | 14263798.4327 | 6120318.863 | 6086648.0123 | 7617838.5681 | 13091546.5281 | 13466408.8826 | 13090157.4505 | 12836166.8898 | 10009607.458 | 7590160.692 | 4449321.3955 | 4295803.9287 | 2831151.005 | 2323453.429 | 0 | 613894697.9997